## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
s1 | s1 | us-001 | Introduction to project | MUST HAVE | No dependency | Avinash | 3- Completed
s2 | s2 | us-001 | Working flow of project | MUST HAVE | No dependency | Avinash | 3- Completed
s3 | s3 | us-001 | information to dask,dask uses, and purpose | MUST HAVE | No dependency | Avinash | 3- Completed
s4 | s4 | us-001 | Information about schema,config files,virtual Environment | MUST HAVE | vscode | Avinash | 3- Completed
s5 | s5 | us-001 | creationof project structure | MUST HAVE | No dependency | Avinash | 3- Completed
s6 | s6 | us-001 | Creation of dask,collected log data | MUST HAVE | No dependency | Avinash | 3- Completed
s7 | s7 | us-001 | Converstion of unstructured data into structured | MUST HAVE | No dependency | Avinash | 3- Completed
s8 | s8 | us-001 | Real time ingestion and parsing of large scale logs | MUST HAVE | vscode | Avinash | 3- Completed
s9 | s9 | us-001 | Information about regular expression | MUST HAVE | vscode | Avinash | 3- Completed
s10 | s10 | us-001 | Execution of project | MUST HAVE | vscode | Avinash | 3- Completed
s11 | s11 | us-001 | Injecting and distributing processing modules | MUST HAVE | No dependency | Avinash | 3- Completed
s12 | s12 | us-001 | Information about metadata,pipeline.code of preprocessing execution | MUST HAVE | vscode | Avinash | 3- Completed
s13 | s13 | us-001 | Introduction to milestone 3,Anomoly detection | MUST HAVE | No dependency | Avinash | 3- Completed
s14 | s14 | us-001 | Types of anomaly detection,Alerts. | MUST HAVE | No dependency | Avinash | 3- Completed
s15 | s15 | us-001 | port numbers,status codes | MUST HAVE | No dependency | Avinash | 3- Completed
s16 | s16 | us-001 | Standard Deviation,z-score | MUST HAVE | No dependency | Avinash | 3- Completed
s17 | s17 | us-001 | Implementation of Anamoly detection code | MUST HAVE | vscode | Avinash | 3- Completed
s18 | s18 | us-001 | Code explanation of anamoly detection | MUST HAVE | vscode | Avinash | 3- Completed
s19 | s19 | us-001 | code explanation of anamoly detection | MUST HAVE | vscode | Avinash | 3- Completed
s20 | s20 | us-001 | Information about streamlit | MUST HAVE | No dependency | Avinash | 3- Completed
s21 | s21 | us-001 | Exection of stereamlit | MUST HAVE | vscode | Avinash | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7