## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
s1 | s1 | us-001 | Introduction to project | MUST HAVE | No dependency | Avinash | 3- Completed
s2 | s2 | us-001 | Working flow of project | MUST HAVE | No dependency | Avinash | 3- Completed
s3 | s3 | us-001 | information to dask,dask uses, and purpose | MUST HAVE | No dependency | Avinash | 3- Completed
s4 | s4 | us-001 | Information about schema,config files,virtual Environment | MUST HAVE | vscode | Avinash | 3- Completed
s5 | s5 | us-001 | creationof project structure | MUST HAVE | No dependency | Avinash | 3- Completed
s6 | s6 | us-001 | Creation of dask,collected log data | MUST HAVE | No dependency | Avinash | 3- Completed
s7 | s7 | us-001 | Converstion of unstructured data into structured | MUST HAVE | No dependency | Avinash | 3- Completed
s8 | s8 | us-001 | Real time ingestion and parsing of large scale logs | MUST HAVE | vscode | Avinash | 3- Completed
s9 | s9 | us-001 | Information about regular expression | MUST HAVE | vscode | Avinash | 3- Completed
s10 | s10 | us-001 | Execution of project | MUST HAVE | vscode | Avinash | 3- Completed
s11 | s11 | us-001 | Injecting and distributing processing modules | MUST HAVE | No dependency | Avinash | 3- Completed
s12 | s12 | us-001 | Information about metadata,pipeline.code of preprocessing execution | MUST HAVE | vscode | Avinash | 3- Completed
s13 | s13 | us-001 | Introduction to milestone 3,Anomoly detection | MUST HAVE | No dependency | Avinash | 3- Completed
s14 | s14 | us-001 | Types of anomaly detection,Alerts. | MUST HAVE | No dependency | Avinash | 3- Completed
s15 | s15 | us-001 | port numbers,status codes | MUST HAVE | No dependency | Avinash | 3- Completed
s16 | s16 | us-001 | Standard Deviation,z-score | MUST HAVE | No dependency | Avinash | 3- Completed
s17 | s17 | us-001 | Implementation of Anamoly detection code | MUST HAVE | vscode | Avinash | 3- Completed
s18 | s18 | us-001 | Code explanation of anamoly detection | MUST HAVE | vscode | Avinash | 3- Completed
s19 | s19 | us-001 | code explanation of anamoly detection | MUST HAVE | vscode | Avinash | 3- Completed
s20 | s20 | us-001 | Information about streamlit | MUST HAVE | No dependency | Avinash | 3- Completed
s21 | s21 | us-001 | Exection of stereamlit | MUST HAVE | vscode | Avinash | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Us0001 | task-01 | why do we need conflict files | 2026-02-05 | 2026-02-06 | Jangili srividya | Learned purpose of conflict files in version control | Completed
Us0001 | task-02 | How to create virtual environment | 2026-02-06 | 2026-02-07 | Jangili srividya | Created and configured Python virtual environment | Completed
Us0001 | task-03 | Explore Regular expression in python | 2026-02-12 | 2026-02-13 | Jangili srividya | Practiced regular expressions in Python | Completed
Us0001 | task-04 | Explore about strip(),groupdict() | 2026-02-13 | 2026-02-13 | Jangili srividya | Explored string functions strip() and groupdict() | Completed
Us0001 | task-05 | Explore about ray | 2026-02-24 | 2026-02-25 | Jangili srividya | Studied basics of Ray framework | Completed
Us0001 | task-06 | what is metadata | 2026-02-26 | 2026-02-27 | Jangili srividya | Understood concept of metadata | Completed
Us0001 | task-07 | what is json data | 2026-02-26 | 2026-02-27 | Jangili srividya | Learned JSON data structure and usage | Completed
Us0001 | task-08 | create a email config file,code to connect python | 2026-03-04 | 2026-03-05 | Jangili srividya | Implemented email configuration using Python | Completed
Us0001 | task-09 | explore about smpt,port numbers | 2026-03-05 | 2026-03-06 | Jangili srividya | Explored SMTP and port numbers | Completed
Us0001 | task-10 | streamlit file upload and dropdown | 2026-03-18 | 2026-03-19 | Jangili srividya | Developed Streamlit file upload and dropdown feature | Completed
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
sprint 1 | Day 19 | Milestone 1 review | cleared doubts reagrding
sprint 2 | Day 26 | Agile Temple confusion | Explain how to edit the agile
sprint 2 | Day 33 | Milestone review | project execution
sprint 3 | Day 40 | Email Connection | clarified doubts regarding email
sprint 3 | Day 47 | streamlit | explained about streamlit
sprint 4 | Day 51 | Project execution nd ppt | helped cleared error

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | s1 | 2026-02-02 | 2026-02-06 | Jangili Srividya | Understand project basics | Stop blindly reading theory without trying code | Continue completing assigned tasks on time | Planned tasks before execution
2 | s2 | 2026-02-09 | 2026-02-13 | Jangili Srividya | Learn Dask basics and log data handling | Stop confusion between tools without clarity | Continue hands-on practice | Practiced small implementations
3 | s3 | 2026-02-16 | 2026-02-20 | Jangili Srividya | Learn Regular Expressions | Stop delaying implementation | Continue learning by doing | Practiced regex with examples
4 | s4 | 2026-02-23 | 2026-02-27 | Jangili Srividya | Work on anomaly detection concepts | Stop focusing only on theory | Continue improving coding logic | Improved understanding of data pipeline
5 | s5 | 2026-03-02 | 2026-03-06 | Jangili Srividya | Execute full project workflow | Stop poor time management | Continue integrating all modules | Built Streamlit interface
6
7